## Gantt Chart
Development Gantt Chart
Concrete sprint activities based on the project timeline, team roles, and 10 MVP user stories
Task | Responsible Role | Time | 18 May |  |  | 25 May |  |  | 1 Jun |  |  | 8 Jun |  |  | 15 Jun |  |  | 22 Jun |  |  | 29 Jun |  |  | 6 Jul |  |  | 13 Jul |  | 20 Jul | 27 Jul | 2 Aug |  | 7.Aug
Week 1: Orientation, Product Framing, Technical Plan
Project kickoff and idea framing | Product UIUX Lead
Team roles and collaboration setup | Scrum master
MVP scope and architecture outline | Product UIUX Lead / Backend Lead
Sprint 1: Exploration, Requirements, Data Setup
User research and interview workflow | Product UIUX Lead
User story validation and acceptance criteria | Product UIUX Lead
Product mock-up v1 | Product UIUX Lead
Frontend and mobile framework selection | Frontend Lead / Mobile Lead
Dataset search and quality check | Data & ML Lead
Backend API contract draft | Backend Lead
Sprint 1 milestone | Scrum master | [9 empty] | ◆
Sprint 2: MVP Prototype
Requirement engineering | Product UIUX Lead
Basic backend API prototype | Backend Lead
Basic frontend screens and navigation | Frontend Lead
Mobile app flow and core screens | Mobile Lead
Data cleaning and baseline analytics | Data & ML Lead
US1&US8: Map View with Nearby Activity and Busyness | Backend Lead / Frontend Lead / Mobile Lead / Data & ML Lead
US6& US11: User Login | Backend Lead / Frontend Lead / Mobile Lead / Data & ML Lead
US2& US9: List Last-Minute Student Discounts (if we have time, we could do it, if not we put it into the next sprint) | Backend Lead / Frontend Lead / Mobile Lead / Data & ML Lead
Frontend & Backend Integration v1 | Backend Lead / Frontend Lead / Mobile Lead
Sprint 3: MVP Connection and Model Integration
Requirement engineering | Product UIUX Lead
US3: Plan Transportation to an Event | Backend Lead / Frontend Lead / Mobile Lead / Data & ML Lead
US12:Venue Listing for Last-Minute Availability | Backend Lead / Frontend Lead / Mobile Lead / Data & ML Lead
US5:AI-Generated Activity Summary | Backend Lead / Frontend Lead / Mobile Lead / Data & ML Lead
Model baseline and evaluation loop | Data & ML Lead
Frontend and Backend and Database integration v2 | Backend Lead / Frontend Lead / Mobile Lead / Data & ML Lead
Product backlog refinement | Product UIUX Lead
MVP connected milestone | Scrum master | [21 empty] | ◆
Sprint 4: Rest and Additional Features, Integration Testing, Usability Testing
requirement engineering | Product UIUX Lead
US4: Accessibility-Friendly Transportation and Venue Discovery | Backend Lead / Frontend Lead / Mobile Lead / Data & ML Lead
US7: Discover Affordable Nearby Activities | Backend Lead / Frontend Lead / Mobile Lead / Data & ML Lead
US10: Mobile App Redirect (QR Code) | Backend Lead / Frontend Lead / Mobile Lead / Data & ML Lead
Model and data quality improvements | Data & ML Lead
Integration v3 | Backend Lead / Frontend Lead / Mobile Lead
Deployment preparation | Backend Lead / Frontend Lead
Sprint 4 milestone | Scrum master | [26 empty] | ◆
Sprint 5: Polish and Final Delivery
MVP polish and finalization | Backend Lead / Frontend Lead / Mobile Lead / Data & ML Lead
Additional features after discussions | All
UI polish and bug fixing | Frontend Lead / Mobile Lead
Final report writing | Product UIUX Lead
Repository cleanup | Backend Lead / Mobile Lead
Final submission | Scrum master | [30 empty] | ◆
■ | Product & UX |  |  | ■ | Data & ML |  | ■ | Frontend |  | ■ | Mobile App |  | ■ | Backend |  | ■ | Integration |  | ■ | Team Leads |  | ■ | Sprint |  | ■ | Milestone

## Team Legend
Team Leads and Color Legend
Role | Lead | Timeline Label | Color
Product UIUX Lead | Xiya | Product & UX
Backend Lead | Dan | Backend
Frontend Lead | Sayli | Frontend
Mobile Lead | zk | Mobile App
Data & ML Lead | Erwan | Data & ML
Scrum master | rotation | Scrum Master