## Dan
Date | Task: (Backend Lead) | Description | Time(in Hours) | Cost | Sum_Time | Sum_Cost
18.May | Kickoff | Kickoff | 8 | 200 | 180 | 4500
19.May | Workshop | Initialization | 8 | 200
20.May | Workshop | Initialization | 8 | 200
21.May | Workshop | Idea + Presentation | 8 | 200
22.May | Group meeting | Contract + Business Plan | 4 | 100
23.May |  |  |  | 0
24.May |  |  |  | 0
29.May | Prof Meeting | Prep + Research | 3 | 75
30.May |  |  |  | 0
31.May | Backend Design | File manager choice, database ORM, and others. Creating archetecture etc. | 4 | 100
1.June | Database Design | Setting up supabase and verifying the database structure. | 4 | 100
2.June | Group Meeting |  |  | 0
3.June |  |  |  | 0
4.June | Set up endpoints | Setting up endpoints | 5 | 125
5.June | Meeting With Prof |  | 2 | 50
6.June | Figuring out endpoints | Started to figure out what endpoints we need, realised we need Auth first | 3 | 75
7.June | Started work on Auth | Realised we need both Authorisation and Authentification | 3 | 75
8.June | Finished Auth | Auth working, now need to finish Endpoints | 3 | 75
9.June | Meeting |  | 3 | 75
10.June | Finished Endpoints | Did all the basic endpoints so that Frontend can start working away | 4 | 100
11.June | Deployment + Improve | Started to work on setting up render + optimising filtering for endpoints | 3 | 75
12.June | Meeting Prof Online | Deployed backend. Works well | 3 | 75
13.June | Testing | Started to work on Backend Tests |  | 0
14.June |  |  |  | 0
15.June |  |  |  | 0
16.June | Group Meeting |  | 3 | 75
17.June |  |  |  | 0
18.June | Supabase Auth | Fixign Authentification | 4 | 100
19.June | 1st presentation |  | 5 | 125
20.June |  |  |  | 0
21.June |  |  |  | 0
22.June | Dashboard API | Creating the dashboard API | 4 | 100
23.June | Online meeting |  | 1 | 25
24.June | dashboard api | Finishing with dashboard api and pushing it | 4 | 100
25.June |  |  |  | 0
26.June | Online meeting w prof |  | 1 | 25
27.June |  |  |  | 0
28.June |  |  |  | 0
29.June | Fixing backend | Adding URL image for events and fixing datetime issues | 3 | 75
30.June | Online Meeting |  | 1 | 25
1.July | Prep presentation |  | 6 | 150
2.July | Prep presentation |  | 6 | 150
3.July | Presentation |  |  | 0
4.July |  |  |  | 0
5.July | Fully creating testing | setting up the style of test | 3 | 75
6.July | Creating and finalising test |  | 6 | 150
7.July | Online meeting |  | 1 | 25
8.July |  |  |  | 0
9.July |  |  |  | 0
10.July | Meeting With Prof |  | 1 | 25
11.July |  |  |  | 0
12.July |  |  |  | 0
13.July |  |  |  | 0
14.July | Online Meeting |  | 1 | 25
15.July | Stripe | Adding payment system | 4 | 100
16.July | Stripe | Adding payment system | 4 | 100
17.July | Presentation (Not me) |  | 4 | 100
18.July | Adding payment testing |  | 3 | 75
19.July |  |  |  | 0
20.July | Paper | Figuring out the writes up (my part of the paper) | 2 | 50
21.July | Online Meeting |  | 1 | 25
22.July | Interview Prototype | 3 interviews | 3 | 75
23.July | Diagram | Drawing diagram for the paper | 2 | 50
24.July | Online meeting with prof | Meeting seeing what we will do about demo and paper | 2 | 50
25.July | Demo Prep | Outlining idea + speach | 4 | 100
26.July | Demo Prep | creating videos plus admin and powerpoint | 4 | 100
27.July | Demo Prep | Practising | 4 | 100
28.July | Demo | Explained it 20 times | 6 | 150
29.July | Preping for interview | Revising everything i did | 6 | 150
30.July | Interview itself |  | 1 | 25
31.July |  |  |  | 0
2026-08-01 |  |  |  | 0
2026-08-02 |  |  |  | 0
2026-08-03 | Fixing things | Creating test API + fixing backend repo | 4 | 100
2026-08-04 |  |  |  | 0
2026-08-05 |  |  |  | 0
2026-08-06 |  |  |  | 0
2026-08-07 |  |  |  | 0

## Xiya
Date | Task: (Product UI/UX lead) | Description | Time | Cost | Sum_Time | Sum_Cost
18.May | Kickoff | Kickoff | 8 | 200 | 151 | 3775
19.May | Workshop | Initialization | 8 | 200
20.May | Workshop | Initialization | 8 | 200
21.May | Workshop | Idea + Presentation | 8 | 200
22.May | Group meeting | Contract + Business Plan | 4 | 100
| Linear Initialization | Linear setup + Preparation of Contract&Business Plan | 2 | 50
| Budgetplan Initialization | Excel | 2 | 50
23.May |  |  |  | 0
24.May |  |  |  | 0
26.May | User Story | Develop the first version of user story | 3 | 75
| Sprint planning | Plan the first sprint | 1 | 25
| Team meeting | Plan the meeting, generate the note and update todo list | 2 | 50
28.May | Prepare for the talk with professor | Prepare for the talk with professor | 2 | 50
| Group meeting and generate the meeting notes | Generate meeting notes and talk about the datasets, backend software and MVP | 3 | 75
29.May | Prof Meeting | Prep + Research | 3 | 75
1.June | Interview | Talk with 3 students about the general ideas | 1 | 25
| Questionaire | Prepare the questionaire with google form | 2 | 50
| Mockup | Design the first mockup for web and mobilep platform | 2 | 50
2.June | Mockup | Design the first mockup for web and mobilep platform | 7 | 175
| Group meeting and generate the meeting notes | Prepare the meeting, attend the meeting and generate the meeting notes | 2 | 50
4.June | update User Story | After reviews, 10 user stories are prioritized | 4 | 100
| update Businessplan | Update gantt chart and details | 3 | 75
5.June | meeting with tutor and teammates | talk about the prototype, sprint planning, presentation, user stories | 1 | 25
8.June | Mockup, questionaire and sprint planning | finalize the questionaire in google form, sort out the mockup and reference code, finalize the sprint planning structure | 5 | 125
9.June | Meeting |  | 3 | 75
10.June | Backlog + Ganttchart | Update the backlog and ganttchart | 2 | 50
15.June | Presentation | Preparation | 4 | 100
17.June | Presentation | Preparation | 4 | 100
18.June | Presentation | Preparation | 1 | 25
19.June | Presentation + sprint review + group meeting | Preparation | 4 | 100
25.June | Backlog + Timesheet + CI | Update | 1 | 25
26.Jun | Backlog + Group Meeting + CI + Metting with Professor | Update | 4 | 100
30.Jun | CI and Test for data | Update | 1 | 25
2026-07-03 | Sprint Review + Presentation | Attend | 5 | 125
10.Jul | Meeting + Report Structure | Attend the meeting and organize the report | 2 | 50
13.Jul | Organize the Backlogs in linear | Sort the backlogs | 2 | 50
14.Jul | 1 draft of report | write the report | 4 | 100
15.Jul | improve the ML model | improve the features and models | 4 | 100
17.Jul | frontend presentation+sprint review+group meeting+user interview questions+sort the backlogs | rest stuffs | 7 | 175
23.Jul | Interview with friends | write down the result of interview | 3 | 75
24.Jul | Sprint review + group meetings | discuss the demo | 1 | 25
25.Jul | Report + Summarize the user interviews + update linear | Update | 2 | 50
27.July | Demo + interview | Preparation for demo & interview | 4 | 100
30.July | Interview | Preparation for interview | 3 | 75
31.July | CI update | CI update | 1 | 25
2026-08-03 | Linear finalization | Sort the backlogs and finalize the documentation | 2 | 50
2026-08-04 | Report refinement | Refine the report, such as the logic, language and add the footnote as required | 4 | 100
2026-08-05 | Delivery checklist | check the delivery and ensure the requirement | 2 | 50

## Sayli
Date | Task: : (Web Frontend Lead) | Description | Time | Cost | Sum_Time | Sum_Cost
18.May | Kickoff | Kickoff | 8 | 200 | 102 | 2550
19.May | Workshop | Initialization | 8 | 200
20.May | Workshop | Initialization | 8 | 200
21.May | Workshop | Idea + Presentation | 8 | 200
22.May | Group meeting | Contract + Business Plan | 4 | 100
23.May |  |  |  | 0
24.May |  |  |  | 0
29.May | Web App (Usage) | Rough Decision (Implementation of Web App for B2B) | 2 | 50
30.May |  |  |  | 0
31.May | Web Frontend Design | Learning/comparing the frameworks to implement the frontend part | 3 | 75
1.June |  |  |  | 0
2.June | Group Meeting | Start with investigation of CI/CD | 1.5 | 37.5
0
4.June | web app design | Learn the framework to implement the web-frontend part | 3 | 75
5.June | Group Meeting | create basic home page | 1.5 | 37.5
6.June |  |  |  | 0
7.June | web app design | implement the frameworks in frontend | 3 | 75
8.June |  |  |  | 0
9.June | Meeting |  | 1 | 25
10.June | web app development | Setup all core enviroment(react19+typescript+leaflet) | 4 | 100
11.June | web app development | Display the map and Implement one of GET /events/ API on mobile | 5 | 125
12.June | Meeting Prof Online |  | 2 | 50
13.June |  |  |  | 0
14.June | web app dev | login+signup+home page (fix the siignup issues) | 3 | 75
15.June |  |  |  | 0
16.June | Group Meeting |  | 2 | 50
17.June
18.June | web app dev | fix the login and sign up issue | 2 | 50
19.June
20 June
21 June | web app dev | implement dashboard page for organization | 2 | 50
22 June | web app dev | implement other pages-Profile, Settings | 3 | 75
23 June
24 June
25 June | web app dev | Implementation of Dark Mode(In Progress) | 2 | 50
29.June | web app dev | venue details page | 3 | 75
30.June | Group Meeting |  | 1 | 25
1.July |  |  |  | 0
2.July |  |  |  | 0
3.July | Sprint review |  | 1 | 25
3 July | 4 July |  | 1 | 25
6 July | web app dev | Heatmap and ML model implementation in the frontend with images | 2 | 50
7 July | web app dev | Fallback image from ticketmaster, Unsplash based on category if image url is not present in the DB | 1 | 25
8 July | web app dev | Fix the login issues(issues during a new signup) | 1 | 25
9 July | web app dev | Work on the AI summary and description | 2 | 50
12 July | web app dev | fix the map (use inbuilt map instead of the google maps) | 2 | 50
14 July | web app dev | Group Meeting | 1 | 25
15 July | web app dev | Prepare for the presentation(web app) | 3 | 75
16 July | web app dev | Fix the create listing(Dashboard), add event creation, Final touchup to the presentation | 2 | 50
17 July | web app dev | Add the event status and fix the dashobard reload error | 1 | 25
18 July | web app dev | AI Summary implementation(Gemini API key), small map on the event page | 1 | 25
21 July | web app dev | Work and research on the project report | 1 | 25
24 July | web app dev | Sprint review + Project Group meeting | 1 | 25
27.July | Demo + interview | Preparation for demo & interview | 2 | 50
29.July | Interview | Preparation for interview | 2 | 50
2026-08-04 | Github Repo | Setup and clean the repo | 1 | 25
2026-08-05 | GitHub Repo | Finalize the repo and add everything necessary, fix the CI/CD | 3 | 75

## zk
Date | Task:(Mobile Lead) | Description | Time | Cost | Sum_Time | Sum_Cost
18.May | Kickoff | Kickoff | 8 | 200 | 85.5 | 2137.5
19.May | Workshop | Initialization | 8 | 200
20.May | Workshop | Initialization | 8 | 200
21.May | Workshop | Idea + Presentation | 8 | 200
22.May | Group meeting | Contract + Business Plan | 4 | 100
23.May |  |  |  | 0
24.May | Mobile app design | Learn about the fundamental knowledge about Dart language | 5 | 125
30.May | Git workflow | Initialize a new group repository locally and push it to GitHub | 1 | 25
1.June |  |  |  | 0
2.June | Group Meeting | Start with investigation of Github workflow | 1.5 | 37.5
| Group Meeting |  |  | 0
4.June | Mobile app design | Learn the framework to implement the mobile part | 4 | 100
5.June | Group Meeting | Sprint 1 checkpoint and get feedback from tutor | 1 | 25
6.June |  |  |  | 0
7.June | Mobile app design | Decide the framework of mobile project | 2 | 50
8.June |  |  |  | 0
9.June | Meeting |  | 1 | 25
10.June | Mobile app development | Setup all core enviroment and build the Scafford of moblie end. | 4 | 100
11.June | Mobile app development | Display the map and Implement one of GET /events/ API on mobile | 4 | 100
12.June | Meeting Prof Online |  | 3 | 75
13.June |  |  |  | 0
14.June |  |  |  | 0
15.June |  |  |  | 0
16.June | Group Meeting |  |  | 0
17.June |  |  |  | 0
18.June | Mobile dev | Deploy mobile on netlify | 2 | 50
19.June | Mobile dev | Implement inside- app route | 2 | 50
0
25.June | Mobile app
29.June | Mobile app | Develop saved part and venue details page | 3 | 75
30.June | Group Meeting |  | 1 | 25
1.July
2.July
3.July | Sprint review |  | 1 | 25
| group meeting |  | 1 | 25
| Mobile app | Fix DNS cache issue | 2 | 50
16.July | Mobile Presentation | Prepare mobile presentation | 4 | 100
17.July | Mobile Presentation |  | 1 | 25
| Group meeting | Discuss some tech issues and set following goals | 2 | 50
| Sprint Review |  | 1 | 25
18.July | Adding payment testing |  | 3 | 75
19.July |  |  |  | 0
20.July | Paper work | Figuring out the writes up (my part of the paper) | 2 | 50
21.July | Online Meeting |  | 1 | 25
22.July | Mobile dev | Change theme to make sure all platforms are the saem | 1 | 25
23.July | Diagram | Drawing diagram for the paper | 2 | 50
24.July | Online meeting with prof | Meeting seeing what we will do about demo and paper | 2 | 50
25.July | Interview Prototype | 3 interviews | 3 | 75
26.July |  |  |  | 0
27.July |  |  |  | 0
28.July | Paper work | Write the mobile methodology and reference | 2 | 50
29.July | Interview Prep | Prepare the final Interview question | 2 | 50
30.July | Interview Prep | Interview day | 0.5 | 25
31.July |  |  |  | 0
2026-08-01 |  |  |  | 0
2026-08-02 |  |  |  | 0
2026-08-03 |  |  |  | 0
2026-08-04 | Github repo | Change the repository visibility and set up branches protection rules | 2 | 50
2026-08-05 |  |  |  | 0
2026-08-06 |  |  |  | 0
2026-08-07 |  |  |  | 0

## Erwan
Date | Task: (Data ML lead) | Description | Time | Cost | Sum_Time | Sum_Cost
18.May | Kickoff | Kickoff | 8 | 200 | 154 | 3850
19.May | Workshop | Initialization | 8 | 200
20.May | Workshop | Initialization | 8 | 200
21.May | Workshop | Idea + Presentation | 8 | 200
22.May | Group meeting | Contract + Business Plan | 4 | 100
23.May |  |  |  | 0
24.May |  |  |  | 0
26.May | Group Meeting |  | 1 | 25
27.May | Testing Plan | Creating Testing Plan for group members | 3 | 75
29.May | Prof Meeting | Prep | 2 | 50
1.June | Data | Investigating possible datasets | 4 | 100
2.June | Data | Investigating possible datasets | 4 | 100
3.June | Data | Investigating possible datasets | 4 | 100
4.June | Data | Start cleaning datasets | 4 | 100
5.June | Data | Cleaning datasets | 4 | 100
8.June | Data | Create pipeline | 4 | 100
9.June | Data | Create pipeline | 4 | 100
10.June | Data | Investigate modelling | 4 | 100
18.June | API | Look into Ticketmaster API | 3 | 75
19.June | API | Populate Venues | 3 | 75
22.June | API | Populate Events | 3 | 75
23.June
24.June | Model | Train model | 4 | 100
25.June | Model | Fine-tune model | 4 | 100
26.June | Model | Create new features | 8 | 200
29.June
30.June | Meeting | Online Meeting | 1 | 25
1.July | Prep Presentation |  | 4 | 100
2.July | Prep Presentation |  | 4 | 100
3.July | Presentation
4.July | DB & API | Add zones to DB+API Code | 3 | 75
6.July | API & Norm | API Code & Norm | 4 | 100
10.July | Meeting | Online Meeting | 1 | 25
13.July | Model |  | 4 | 100
17.July | Meeting + updates | In-person meeting | 4 | 100
20.July | Paper |  | 4 | 100
21.July | Paper |  | 4 | 100
22.July | Paper + interview |  | 5 | 125
23.July | Paper |  | 3 | 75
24.July | Meeting | Online meeting | 1 | 25
25. July | Demo + interview | Preparation for demo & interview | 3 | 75
27.July | Demo + interview | Preparation for demo & interview | 4 | 100
28.July | Interview | Preparation for interview | 3 | 75
2026-08-04 | GitHub | Finalize GitHub repo | 3 | 75